# SpeedTruth, Path to Ministry Adoption

An honest map of what stands between this submission and a transport ministry using it in practice. We state the gaps openly rather than imply the tool is deployment-ready.

Where it is today: a validated, reproducible, FDUA-compliant analytical pipeline that turns standard probe + open data into a per-segment Speed Safety Score, an interactive decision map, a costed work-list, and an automated imagery-based road-condition check. It is a decision-support prototype, not yet an operational system.

## What a ministry needs before it can rely on this

| # | Missing piece | Why it’s needed | When | Owner |
| --- | --- | --- | --- | --- |
| 1 | Posted-limit ground truth, field-audit a stratified sample to calibrate the unvalidated limit field | The limit field is a commercial estimate; the model currently flags for review, not action | Refinement (weeks) | Team + ministry survey unit |
| 2 | Outcome linkage, corridor-level trauma admissions / insurance claims / police crash coordinates, pre-registered before testing | Converts the score from theoretical-risk to evidence-anchored; closes the validation gap | Refinement (weeks–months) | Ministry + health/insurance data owners |
| 3 | Full-network imagery coverage, fill Mapillary gaps (commissioned drive or dashcam programme) | Today ~24% of segments have imagery for the CV layer; the rest fall back to the proxy | Refinement | Team + ministry |
| 4 | Certified-coder CV validation, independent iRAP-trained raters on a statistically meaningful held-out sample, with inter-rater statistics | Lifts the road-condition layer from “consistency-checked” to professional-grade | Refinement | iRAP-style assessor |
| 5 | Corridor aggregation, DELIVERED in this submission (CORRIDORS.md): flagged segments clustered into contiguous same-road corridors; top 20% hold ~76% of benefit | Matches the unit of decision and budgeting | Done | Team |
| 6 | GIS / workflow integration, rebuild on ADB’s GIS platform and export to the ministry’s existing system; define the standing limit-review mechanism (trigger rules, ownership, review cadence) | Makes it a recurring process, not a one-off report | Finalist stage | Team + ADB + ministry |

## A credible 90-day path (if shortlisted)

- Weeks 1–3: corridor aggregation; commission/secure one outcome proxy and pre-register the convergence test; recruit an independent CV coder.

- Weeks 4–8: field-audit a limit-calibration sample; run the certified-coder validation; report the confusion matrix and failure modes.

- Weeks 9–12: rebuild outputs on the ADB GIS platform; co-design the limit-review workflow with a ministry counterpart; deliver a corridor-level investment plan with local unit costs.

We are explicit that items 1, 2 and 4, the ones that would most change a funding decision, are not achievable in the application window and are the core of the refinement-stage work.